## Task and Timeline
Sauce & Spoon Project Plan
Task # | Task | Task Owner | Start Date | Due Date | Duration | Notes | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
[8 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Milestone 1: Project Initiation
1.1 | Align and evaluate stakeholders | Sabthagiri |  |  | 3 |  | 100% | bar: Week 1 M to Week 1 W
1.2 | calculate projections and enhancements | Sabthagiri, Gilly, Alex, Seyduo |  |  | 0 |  | 100% | bar: Week 1 T to Week 1 W
1.3 | Interview members of the staff/ gather historical data on ordering process | Sabthagiri, Gilly, Alex, Seyduo |  |  | 1 |  | 100% | bar: Week 1 W
1.4 | Create project charter (scope and goals) | Sabthagiri |  |  | 0 |  | 100% | bar: Week 1 W to Week 1 F
1.5 | Schedule kick off meeting | Sabthagiri |  |  | 0 |  | 100% | bar: Week 1 T
2 | Milestone 2: Tablet Research/Sourcing
2.1 | Researchtablet customization options/compatible operating system with existing POS | Seydou |  |  | 4 | Depends on if we have 3.0 or older, I think ours might be order | 100% | bar: Week 1 T to Week 2 T
2.3 | Find and generate quotes | Deanna |  |  | 3 |  | 100% | bar: Week 1 F to Week 2 T
2.4 | Choose a tablet system | Seydou |  |  | 2 |  | 100% | bar: Week 2 W
2.5 | Determine how many tablets we need to order for each location with General Managers | Alex, Gilly |  |  | 0 |  | 100% | bar: Week 2 W
2.6 | dtermine if we will purchase and store backup tablets for emergencies | Seydou |  |  | 0 |  | 100% | bar: Week 2 W
2.7 | Select top 3 vendor for branding with marketing team | Deanna, Seydou |  |  | 1 |  | 100% | bar: Week 2 W
2.8 | Create contract and statements of work for vendors (timeline, deliverables, installation/writing schedule) | Deanna |  |  | 4 |  | 100% | bar: Week 2 W to Week 3 M
2.9 | Finalize and get contracts and statements of works signed | Deanna |  |  | 2 |  | 100% | bar: Week 2 F to Week 3 M
2.1 | Schedule & hold Phase I Meeting (progress and task estimation) | Sabthagiri |  |  | 0 |  | 100% | bar: Week 2 W
3 | Milestone 3: General Project Planning | 0
3.2 | Message about launch date to stakeholder | Sabthagiri |  |  | 0 |  | 100% | bar: Week 3 T
3.3 | Project plan Updates | Sabthagiri |  |  | 13 |  | 100% | bar: Week 3 T to Week 5 T
3.4 | Outline design draft dates with marketing team | Seydou |  |  | 2 |  | 100% | bar: Week 3 T to Week 3 W
3.5 | Create initial launch date plan: Staffing, Troubleshooting, etc. | Deanna |  |  | 2 |  | 100% | bar: Week 3 T to Week 3 W
3.6 | Create a post-dining survey to access customer satisfaction and establish metrics | Sabthagiri |  |  | 3 |  | 100% | bar: Week 3 W to Week 3 F
2.1 | Phase II Meeting (progress and task estimation) | Sabthagiri |  |  | 0 |  | 100% | bar: Week 6 T
4 | Milestone 4: Tablet Customization/Shipping/Installation
4.1 | Create a Initial rough mockup for menu layout with coupon links | Carter |  |  | 5 | Still waiting, need update from Carter. Once recieved estimate from Mult. team members | 100% | bar: Week 4 M to Week 4 F
4.4.1 | Work with tablet vendor on custom branding, design, and uploading menus to tablets | Sydou |  |  |  | The vendor has done this many times, received estimate from mult, team members | 100% | bar: Week 4 M
4.4.2 | * Order two tablets for both locations (For test run) | Deanna |  |  | 0 |  | 100% | bar: Week 4 M
4.4.3 | Two test tablets shipping from warehouse | Seydou |  |  | 10 | *Seydou projected 7-10 days shipping timeline, 3-4 hours to integrate the POS systems has to ship from further away warehouse, adds a few days | 100% | bar: Week 4 M to Week 5 F
4.4.4 | Determine specific bar location for installation with GMs for North & Downtown | Seydou |  |  | 0 |  | 100% | bar: Week 4 T
4.5 | Conform tablet arrival, initial quality, test menu layout | Seydou |  |  | 1 |  | 100% | bar: Week 5 F
4.5 | Schedule elctrician test installation for North and Downtown | Deanna |  |  | 1 |  | 100% | bar: Week 5 F
4.6.1 | Install one yablet to ensure proper installation and to identify any potential issues | Seydou |  |  | 3 |  | 100% | bar: Week 6 M to Week 6 W
4.6.2 | * Finalize order of remaining tablets | Deanna |  |  | 1 |  | 100% | bar: Week 6 W
4.6.3 | Remaining tablets shipping from warehoue | Seydou |  |  | 10 | * Seydou projected 7-10 days shipping timeline, 3-4 hours to integrate the POS systems has to ship from further away warehouse, adds a few days | 100% | bar: Week 6 W to Week 7 T
4.7 | Conform remaining tablets arrival and initial quality test | Sabthagiri, Seydou |  |  | 1 |  | 100% | bar: Week 7 T
4.8 | Schedule elctrician for both North and Downtown | Deanna |  |  | 4 |  | 100% | bar: Week 7 T
4.9 | Install remaining tablets to ensure proper installation and to identify any potential issues | Seydou |  |  | 3 |  | 100% | bar: Week 7 T to Week 8 M
4.1 | Phase III Meeting (progress and task estimation) | Sabthagiri, Seydou |  |  | 0 |  | 100%
4.11 | Project Plan Updates | Sabthagiri |  |  | 13 |  | 100% | bar: Week 7 M to Week 9 W
5 | Milestone 5: Staff training
5.1 | Training GMs on new tablets with Seydou | Seydou,Deanna, Gilly, Alex |  |  | 1 | Seydou will train the GMs for 2 hours each solo training, plus present for staff training incase needed. | 100% | bar: Week 8 T
5.2 | Start drafting training content and schedule possible training dates with GMs and kitchen Managers | Seydou. Gilly, Alex |  |  | 3 |  | 100% | bar: Week 8 T to Week 8 T
5.3 | Pre-training staff Meeting at North location to introduce tablets | Gilly |  |  | 1 |  | 100% | bar: Week 8 T
5.4 | Pre-training to staff Meeting at Downtown loction to introduce tablets | Alex |  |  | 1 |  | 100% | bar: Week 8 T to Week 8 F
5.5 | Confrim traiing dates with GMs and update staff calendars | Alex, Gilly, Carter, Zane, Larissa |  |  | 2 |  | 100% | bar: Week 8 F
5.6 | Complete training content &Run through training content with GNs | Deanna, Gilly, Alex |  |  | 1 | Seydou will provide notes | 100% | bar: Week 8 F
5.8 | Alex Trains the Downtown staff | Alex |  |  | 3 | needs 2 half days at each location to miniize business impact. | 100% | bar: Week 9 M to Week 9 T
5.9 | Gillly trains the North staff | Gilly |  |  | 3 | needs 2 half days at each location to miniize business impact. | 100% | bar: Week 9 M to Week 9 T
5.1 | Zfinalize launch day plam : staffing.trobleshooting,etc. | Deanna, Gilly, Alex |  |  | 1 |  | 100% | bar: Week 9 W
5.11 | Confirm post-dining survey to assess customer satisfaction and metrics | Sabthagiri |  |  | 1 |  | 100% | bar: Week 9 W
5.12 | Phase IV meeting - Pre-Launch Day (progress and task estimation) | Deanna |  |  | 0 |  | 100% | bar: Week 9 T
5.13 | Project Plan Updates | Sabthagiri |  |  | 11 |  | 100% | bar: Week 8 T to Week 10 T
6 | Milestone 6: Test Run/Troubleshoot
6.1 | Test-run of tablets in restaurants with staff family/friends (ordering and surveys) | Deanna |  |  | 1 |  | 100% | bar: Week 10 W
6.2 | Team meeting (troubleshoot plan/support plan) | Deanna, Gms and Seydou |  |  | 1 |  | 100% | bar: Week 10 W
6.4 | Installation any needed upgrades to devices | Sabthagiri |  |  | 3 |  | 100% | bar: Week 10 W to Week 10 F
7 | Milestone 7: launch of Pilot
7.1 | Launch day |  |  |  | 0 |  | 100% | bar: Week 11 M
7.2 | Updates Project Plan | Sabthagiri |  |  | 2 |  | 100% | bar: Week 11 M to Week 11 T
8 | Milestone 8: Post pilot Wrap-up/Project closing
8.1 | Comlete Closing Documentation | Sabthagiri |  |  | 2 |  | 100% | bar: Week 12 W to Week 12 T
8.2 | Retrospective meeting with Management and restaurant staff | Sabthagiri |  |  | 1 |  | 100% | bar: Week 12 F
8.3 | retrospective meeting with leadership/management staff | Sabthagiri |  |  | 1 |  | 100% | bar: Week 12 F

## Project Stakeholders
Stakeholder | Role | Notes
Omar Mubarak | Owner | Responsible for the direction profitability, and reputation of the restaurants group.Most senior stakeholder.
Deanna Coleman | Director of Operations | Responsible fpr daily communication across different teams, Oversees the restaurant managers,Helps with interviewing,hiring, and training new employees.
Carter Ward | Executive Chef | Has the final say on all menu choices, Responsible for overseeing all other chefs employed by the restaurant.
Sabthagiri Kathiravan | Project Manager | Responsible for updating project documents, project charter, project plan, and closing materials.
Gilly Tsodie | General Manager (North) | great resource for trianing and providing input on general restaurant operations . Responsible for hiring and training staff, ordering all the restaurant's supplies, and gauging customer satisfaction at location
Alex Schmidt | General Manager (Downtown) | Previously worked i retail management at a large home improvement chain, Trained by Gilly and Responsible for hiring and training staff, Ordering all the restaurant's supplies, and gauging customer satisfaction at location.
Zane Ductchman | Kitchen Manager (North) | Sous chef kitchen manager - enthusiastic about role,Learning from Larissa and Responsible for : (1) Overseeing daily BOH operations and administrative tasks . (2) Controlling costs and managing labor.
Nia williams | general Manager (Waterfront) | Experience from hostness up to management, Tended bar at a luxury hotel which would be helpful for the pilot, Passionate about the restaurant industry and Responsible forhiring and training staff, o Ordering all the restaurant's supplies, and taking to customers to ensure that they are happy with their service.
larissa Sterin | Kitchen Manager (Downtown) | New to Sauce & Spoon,Previously managed kitchen ata Michelin-star restaurant,Enthusiastic about role and restaurant work and Responsible for : (1) Overseeing daily BOH operations and admistrative tasks (2) Controlling costs and managing labor.
Seydou Diallo | Restaurant Technology consultant | Background in tech support and new to restaurant industry, First major project exited to prove himself and Helps restaurants implement cost-effective,east-to-use,integrated technology systems

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optismistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone 1: Tablet Research/Sourcing
Research tablet customization options |  | 5
General quotes and review costs |  | 5
Find compatible operating system with existing POS |  | 7
Choose a tablet system |  | 3
Find and confirm top vendors for installation and design |  | 7
Vendor timeline and deliverables schedule concerning installation/wiring |  | 5
Create contracts and stamenets of work for vendors |  | 5
Milestone 2: General Project Planning
Message about launch date to stakeholders |  | 3
Project Plan Updates |  | 2
Outline design draft dates with marketing team |  | 1
Create Initial launch day plan: staffing,troubleshooting, etc. | How might tablets affect tips for waistaff? | 3
Create a post-dining survey to assess customer satisfaction and establish metrics |  | 5
Milestone 3: Tablet Customization/Shipping/Installation
Project Plan Updates |  | 3 | 2 | 3 | 4 | M
Design Menu layout - Marketing team and vendor |  | 2
Order two talets for both location (for test run) |  | 1
Two test tablets shipping from warehouse |  | 3
Determine specific bar location for installation with GMs for North and Dwontown |  | 5
Schedule electrician test installation for restaurants |  | 3
Install on tablet at both locations to identify any potentail issues |  | 2
Order of remaining tablets |  | 1
Install remaining tablets at both the locations |  | 7
Milestone 4: Staff training
Train GMs on new tablets with Seydou | Waitstaff trends to resist changing the way they interact with customers, and the tablet benefits aren't always obvious. If someone in-house does the training they're more likely to get on board. So we'll have Seydou train a small group of us, then we'll schedule a second training with all the staff at each location. | 5 | 3 | 4 | 6 | M
Create training content | So its sounds like we'll have you train a small group of us, then we'll schedule a second training with all the staff at each location. | 3
Pre-training prep meeting | In the Past at the Waterfront location: Didn't get waitstaff buy-in before rolled out the reconstructed pay and incentives for the entire staff with no tips (embedded in prices). Staff felt we brought in this new initiative--something that directly affected their pay--without telling them, and half quit to earn more elsewhere. | 2
Run through training content with GMs | If we're implementing something that could affect waitstaff tips. we have to get their buy-in first. And have it come from a GM. Have a staff meeting, or smaller team meetings, and keep messaging | 1
Train staff at both locations | *May be confusion with multiple software interacting | 7 | 4 | 6 | 8 | L
Finalize launch day plan: staffing, troubleshooting, etc. |  | 3
Milestone 5: Testing/troubleshoot
Test-run tablets with real-life senario | Gilly recommends testing out the tablets with friends and family who are unlikely to get upset if there are prolems. | 2
Review test run and troubleshoot |  | 3
Milestone 6: Launch Day
Launch tablets |  | 1
Review first week and make updates |  | 3
Milestone 7: During Pilot
Ensure customer data is being collected and stored |  | 5
Check tablet function at the end of each week |  | 7
Milestone 8: Post Launch
Organize data |  | 3
Analyze data |  | 5
Create dashboard and presentation |  | 1
gPresent findings and survey stakeholders |  | 3
Gather and finalize project documentation |  | 4
Schedule project retrospective |  | 2

## Addtional Resources
Additional Resources
Title | Link | Date Added | Notes
PMi Article "Restaurant Reboot" | https://www.pmi.org/learning/library/restaurant-reboot-9754 | 2024-04-29 | *"Project Management institute" feedback on tablet rollout plan
Tablet POS Systems | https://www.merchantmaverick.com/top-tablet-pos-systems-restaurants/ | 2024-04-30 | "list of "Top 7" in restaurant industry
Best Practices For Your Digital Menu | https://www.barandrestaurant.com/operations/best-practices-your-digital-menu | 2024-05-02 | *ideas for mobile device use
High-Tech hospitality | https://restaurant.org/education-and-resources/resource-library/high-tech-hospitality/ | 2024-05-05 | *Free report on status of tech in restaurant industry
Key restaurant Technology Hacks for Growth in 202 | https://tech.co/news/restaurant-technology-trends | 2024-05-07 | *Has helpful notes on how tablets can decrease waste and increase effeciency.

## Quality and Evaluation
Quality & evaluation
Quality Standards Category | Quality Standards Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met? Y/N
Customer Satisfaction | Increase Customer retention in tablet areas by 5% | Are customers willing to be seated in tablet areas? Are customers having a better experience with new tablets? | By 5% after first month of tablet launch.
Customer Satisfaction | Average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. | Are the customers having a better dining experience with the tablets? | the average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. Decrease the average table turn time by 30 minutes.
Customer Satisfaction | A minute or less average checkout time. | Are the tablets deemed usable by customers? Are the tablets saving time? How quickly are customers learning how to navigate the tablets? Do customers think the tablets have a attractive design? | Checkout time taken for customers is 1 minute or less.
Customer Satisfaction | Less than 5% of customers who use tablets report technical issues eack week. | Do the tablets work as expected? | Less than 5% of customers who use tablets report technical issues each week.
Customer satisfaction | 98% tablets order accuracy. Wait staff can log into tablets accounts on the first try. | Are the customers receiving the correct orders? | 98% of customers receive the correct order. wait staff can log into their tablet account in the first try. Tablet error logs report a maximum of a one error per shift

## Survey Qeustions
Survey Evaluation
Quality Standards Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Question Answer Options (depends on question type)
[5 empty] | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Increase customer retention in tablet areas by 5% | Are customers having a better dining experience with tablets? Are customers willing to be seated in tablet areas? | The number of customers sitting in tablet areas increase by 5% after the first month of tablet launch | How often do you dine with us? | Multiple choice | This was my first time | I visit you occasionally | I come by at least once a month | I dine with you weekly
Average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. | Are customers having a better dining experience with the tablets? | The average ticket time is 8 minutes for appetizer and 12-15 minutes for entrees. | How long did your enitre dining experience take? Please use your best judgement? | Multiple choice | Less than 30 minutes | between 30 and 45 minutes | Betwwen 45 to 1 hour | Between 1 hour to 1.5 hour | More than 1.5 hour
aA minute or less average checkout time. | Are the tablets saving time? | Checkout time for guests is 1 minute or less. | How easy was the tablet for you to use? | Multiple choice | Extremely difficult | Difficult | Neutral | Easy | Extremely Easy
Less than 5% of customers who use tablets report technical issues each week. | Do the tablets work as expected? | Less than 5% of customers who use tablets report technical issues eack week. | Did everyone in your party recieve the correct order? | Yes/No | Yes | No
98% tablet order accuracy | are the customers receicve the correct order? | 98% of customers recieve the correct orders. | How long did you wait between ordering your entree and it's arrival. Please use your best Experience. | Multiple choice | Less than 5 minutes | Between 5 and 10 minutes | Between 10 to 15 minutes | More than 15 minutes | Our order have never arrived. We had to ask someone.
Less than 10 minutes averahe wait time for seating | Are customers being served swiftly? | customers wait time is a maximum of 10 minutes. | How long did you wait in the lobby before being seated? | Multiple choice | 5 minutes or less | Between 5 and 10 minutes | Between 10 to 30 minutes | More than 30 minutes | I had a reservation
|  |  | Did you order any of the reccomended paired items? | Yes/No | Yes | No
|  |  | Were there any errors that occured during your dining experience? | Multiple choice | 0 errors | 1 errors | 2 errors | 3 errors | 4 or more errors
|  |  | would you reccomend dining here with the tablet experience to you friends? | Yes/No | Yes | No
|  |  | Are there any other comments you have related to the tablet experience? if any, please let us konw! | Open-ended | Open-ended
|  |  | Please rank the features of the tablets that you like from highest (1) to lowest (5) | Scaled | pairing eccommendations | the menu page | the check page (where you order and pay) | the games page | the featured items page
|  |  | Your checkout was quick and easy | True/False | TRUE | FALSE
|  |  | Did you use any of our discounts or special offers? | Yes/No | Yes | No
|  |  | Please rank how likely is it that you will visit our restaurant again from highly likely (5) to never visit again (1) | Scaled | 5 - Highly likely | 4 | 3 | 2 | 1 - Highly unlikely