## Slide 1: Stakeholder Analysis
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Note
Omar Mubarak | Owner | H | M | Responsible for the overall direction, and reputation of the restaurant group Most senior stakeholder
Deanna Coleman | Director of Operations | H | H | Responsible for daily communication across different teams. Oversees the restaurant managers Helps with interviewing, hiring, and training new employees.
Carter Ward | Executive Chef | M | H | Has the final say on the menu choices. Responsible for overseeing all other chefs employed by the restaurant.
Gilly Tyson | General Manager (North) | H | H | Great resource for training and providing input on general restaurant operations,responsible for training and hiring staff
Alex Schmidt | General Manager (Downtown) | H | H | Previously worked in retail management at a large home improvement chain. Responsible for hiring and training staff, ordering all the restaurant’s supplies, and gauging customer satisfaction at location

## Slide 2: Stakeholder Analysis
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Note
Nia Williams | General Manager (waterfront) | L | L | Experience from hostess up to management. Tended bar at luxury hotel which would be helpful for the pilot Passionate about the restaurant industry. Responsible for hiring and training staff, staff, ordering all the restaurant and talking to customers to ensure that they are happy with their service.
Zane dutchman | Kitchen Manager (North) | M | H | Sous chef before kitchen manager - enthusiastic about role Learning from Larissa Responsible for : (1) Overseeing daily BOH operations and administrative tasks and (2) Controlling costs and managing labor.
Larissa stein | Kitchen Manager (Downtown) | M | H | New to Sauce & Spoon. Previously managed kitchen at a Michelin-star restaurant. Enthusiastic about role and restaurant work.
Seydou Diallo | Restaurant Technology Consultant | M | H | Background in tech support and new to restaurant industry. First major project and excited to prove himself. Helps restaurants implement cost-effective, easy-to-use, integrated technology systems

## Slide 3
Keep satisfied (high priority) | Manage closely (high effort)
Monitor (minimum effort) | Show consideration
High
med
Low
high
med
low
Omar
Owner
Nia
General Manager-Waterfront
Nia
GM-Waterfront
Omar
Owner
Larissa kitchen Manager - Downtown
Zane Kitchen Manager - North
Deanna Director of operations
Gilly GM-North
Alex
GM - Downtown
Carter Exec - Chef
Seydou Restaurant Consultant
Interest
Power
Stakeholder Analysis

## Slide 4: Stakeholder Analysis Rational
Stakeholder | Priority | Notes
Omar mubarak | Keep satisfied (High priority) | I put Omar at high Power and low interest because he is the owner of Sauce & Spoon and is a senior stakeholder.however, in terms of interest, he has focused on the bigger picture of the restaurant chain.He would likely like weekly updates with overview details on a dashboard, but would not want daily updates with all the details
Deanna Coleman | Manage closely (high effort) | I put Deanna at high power because she has the decision-making power out of all the people that I directly interact with on a regular bases. She is responsible for daily communication across the different teams and oversees the restaurant managers, so she will be instrumental in garnering support getting final approval on decisions. She also helps with interviewing, hiring, and training new employees fir all locations.

## Slide 5: Stakeholder Analysis Rational
Stakeholder | Priority | Notes
Cater Ward | Manage closely (high Priority)/Show Consideration | I put Carter at medium power and medium interest because he has the final say on all menu choices which impact what is on the digital menu and what appetizers are emphasizes . He is responsible for overseeing all other chefs employed by the restaurant. So he would care about what happens at all location but only what impacts kitchen staff. His interest in the project is high, but he isn't involved in day-to-day decision-making
Gilly tyson | Manage closely (high effort) | I put Gilly at high power and high interest because she is responsible for hiring and training staff, ordering all the restaurant supplies, and gauging customer satisfaction at the North location. She will be the expert for the location but defers to deanna in terms of decision-making. The success of the pilot will greatly impact the operations and revenue of the restaurant.

## Slide 6: Stakeholder Analysis Rational
Stakeholder | Priority | Notes
Alex Schmidt | Manage Closely (high effort) | I put Alex at High interest and High Power because he is responsible for hiring and training staff, ordering all the restaurant’s supplies, and gauging customer satisfaction at the Downtown location.He will be the expert for the location but defers to Deanna in terms of decision making. The success of the pilot will greatly impact the operations and revenue of the restaurant. Also, they are excited about selling appetizers since that is a key source of interest for customers in the business district.
Nia Williams | Monitor (minimum effort) | She is responsible for hiring and training staff, ordering all the restaurant’s supplies, and talking to customers to ensure that they are happy with their service at the Waterfront location. She is not directly affected bt the completion of this project. While she may eventually be interested in it when the next project is to expand to other locations.

## Slide 7: Stakeholder Analysis Rational
Stakeholder | Priority | Notes
Zane Dutchman | Show consideration | Zane is medium Interest and Low Power. He is responsible for overseeing daily BOH operations and administrative tasks and controlling costs and managing labor for the North location.While I do want to make sure the tablets positively impact the operations of the kitchen, they have lower power and medium interest.
Larissa Stein | Show consideration | Larissa Zane is medium Interest and Low Power. She is responsible for overseeing daily BOH operations and administrative tasks and controlling costs and managing labor for the North location. While I do want to make sure that the tablets positively impact the operations of the kitchen, they have lower power and medium interest.I do want to note that she trained Zane and may have some influence there.
Seydou Diallo | Manage closely (high effort) | Seydou will be important for helping with the implementation of cost-effective, easy-to-use, and integrated technology systems. While he may not have last say on decision, but he will be extremely important for installing the tablet software and choosing the choosing the correct software for integration.

## Slide 8
Project Role | Name | Title
Project Lead | Sabthagiri Kathiravan | Project Manager
Team Members | Deanna Coleman | Director of Operations
Carter Ward | Executive Chef
Gilly Tyson | General Manager (North location)
Alex Schmidt | General manager (Downtown)
Nia williams | General Manager (Waterfront)
Zane Dutchman | Kitchen manager (North location)
Larissa Stein | Kitchen Manager (Downtown)
Seydou Diallo | Restaurant Technology Consultant